## Cover Page
Home Stay
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Gunjan Kumari | Syed Moosa Kadir | Syed Moosa Kadir
| Role | Programmer Analyst Trainee | Trainer | Trainer
| Signature | Gunjan Kumari
| Date | 2022-01-24
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog Home Stay Project ID: A031 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS |  | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Design registration page | 3 | Keshav | Completed | 8 | 2 | 3 | 2 | 2 | 0
Task_2 | Create and connect to table | 2 | Musaddik | Completed | 3 | 0 | 2 | 1 | 1 | 0
Task_3 | Connection to login page | 2 | Keshav | Completed | 3 | 0 | 0 | 1 | 2 | 1
Task_4 | Exception handling | 1 | Pushpak | Completed | 4 | 0 | 0 | 1 | 0 | 1
US_2 | User Authentication | 8
Task_1 | Design Login page | 3 | Keshav | Completed | 7 | 3 | 1 | 2 | 0 | 1
Task_2 | Retrieve from database | 2 | Musaddik | Completed | 4 | 0 | 1 | 1.5 | 2 | 0
Task_3 | Connection to Action page | 2 | Keshav | Completed | 2 | 0 | 0 | 1 | 2 | 0
Task_4 | Exception handling | 1 | Pushpak | Completed | 4 | 0 | 0 | 0 | 1 | 1
US_3 | Admin Credentials | 8
Task_1 | Store Admin data in database | 3 | Musaddik | Completed | 5 | 0 | 1 | 2 | 2 | 1
Task_2 | Design Admin home page | 3 | Keshav | Completed | 8 | 2 | 2 | 3 | 0 | 0
Task_3 | Exception handling | 2 | Vishal | Completed | 4 | 0 | 0 | 1 | 0 | 0
Task_4
US_4 | Help | 8
Task_1 | Design help page | 2 | Pushpak | Completed | 6 | 1 | 2 | 3 | 2 | 0
Task_2 | Database management | 2 | Musaddik | Completed | 4 | 2 | 1 | 1 | 1 | 0
Task_3 | View request resolutions | 2 | Keshav | Completed | 3 | 0 | 1 | 2 | 0 | 0
Task_4 | Auto-populate date of ticket | 2 | Pushpak | Completed | 3 | 0 | 0 | 1 | 1 | 1
US_5 | Resolve Help Request | 5
Task_1 | View help requests | 3 | Keshav | Completed | 5 | 2 | 1 | 1 | 0 | 1
Task_2 | Show details per request ID | 1 | Pushpak | Completed | 5 | 2 | 1 | 2 | 0 | 0
Task_3 | Database management | 1 | Musaddik | Completed | 4 | 0 | 2 | 1 | 2 | 0
Task_4
US_6 | Feedback Questionnaire | 3
Task_1 | Design feedback form | 3 | Pushpak | Completed | 4 | 0 | 0 | 0 | 0.5 | 1
Task_2
Task_3
Task_4
US_7 | User Feedback | 3
Task_1 | Add data to database | 3 | Musaddik | Completed | 4 | 1 | 0 | 0 | 0 | 1
Task_2
Task_3
Task_4
US_8 | Trigger Review | 3
Task_1 | Auto-trigger feedback form | 3 | Musaddik | Completed | 3 | 0 | 0 | 0 | 0 | 1
Task_2
Task_3
Task_4
US_9 | Log Off | 2
Task_1 | Create Log Off Button | 2 | Pushpak | Completed | 2 | 0 | 0 | 0 | 0 | 1
Task_2
Task_3
Task_4
US_10 | Password Reset/Retrieve User ID | 5
Task_1 | Create pop-up questions | 2 | Keshav | Completed | 4 | 0 | 0 | 1 | 0 | 1
Task_2 | Retrieve data from database | 1 | Musaddik | Completed | 4 | 0 | 0 | 0 | 1 | 1
Task_3 | Update data in database | 2 | Musaddik | Completed | 3 | 0 | 0 | 0 | 1 | 2
Task_4
TOTAL |  | 53 |  |  | 82 | 14 | 18 | 26.5 | 18 | 7

## Sprint -2
Sprint Backlog Home Stay Project ID: A031 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_11 | Add Home Stay Details | 8
Task_1 | Design Add Details page | 3 | Keshav | Completed | 8 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 3 | Musaddik | Completed | 6 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 2 | Pushpak | Completed | 3 | 0 | 0 | 1 | 0 | 2
Task_4
US_12 | Update Home Stay Details | 5
Task_1 | Design Update Details page | 2 | Keshav | Completed | 7 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 2 | Musaddik | Completed | 6 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Pushpak | Completed | 3 | 0 | 1 | 0 | 0.5 | 2
Task_4
US_13 | Add/Update Tour Package | 5
Task_1 | Design add/update tour package page | 2 | Pushpak | Completed | 7 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 2 | Musaddik | Completed | 6 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Vishal | Completed | 3 | 0 | 0 | 1.5 | 0 | 2
Task_4
US_14 | Search for Stay | 5
Task_1 | Configure search | 2 | Pushpak | Completed | 6 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 2 | Musaddik | Completed | 4 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Keshav | Completed | 3 | 0 | 1 | 0 | 2 | 1
Task_4
US_15 | View Tour Package | 5
Task_1 | View Tour Package page | 2 | Keshav | Completed | 5 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 2 | Musaddik | Completed | 4 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Keshav | Completed | 3 | 0 | 1 | 0 | 2 | 1
Task_4
US_16 | Book Stay | 8
Task_1 | Design Booking page | 4 | Keshav | Completed | 7 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 3 | Musaddik | Completed | 5 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Pushpak | Completed | 3 | 0 | 1 | 0 | 2 | 1
Task_4
US_17 | View Booking | 5
Task_1 | Manage view page | 2 | Musaddik | Completed | 6 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 2 | Musaddik | Completed | 4 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Keshav | Completed | 3 | 0 | 1 | 0 | 2 | 1
Task_4
US_18 | View Stay History | 5
Task_1 | Manage view page | 2 | Musaddik | Completed | 6 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 2 | Musaddik | Completed | 4 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Vishal | Completed | 3 | 0 | 1 | 0 | 2 | 1
Task_4
US_19 | Report Generation | 8
Task_1 | Design Report Generation page | 4 | Keshav | Completed | 7 | 3 | 4 | 1 | 0 | 0
Task_2 | Configure Generate | 3 | Pushpak | Completed | 4 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Vishal | Completed | 3 | 0 | 1 | 0 | 2 | 1
Task_4
US_20 | Bill Generation | 8
Task_1 | Design bill generation page | 4 | Keshav | Completed | 6 | 3 | 4 | 1 | 0 | 0
Task_2 | Database Management | 3 | Musaddik | Completed | 4 | 0 | 2 | 1 | 3 | 1
Task_3 | Exception Handling | 1 | Pushpak | Completed | 3 | 0 | 1 | 0 | 2 | 1
Task_4
TOTAL |  | 62 |  |  | 74 | 15 | 33 | 12.5 | 19.5 | 13

## Sprint -3
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task_1
Task_2
Task_3
Task_4
User Story #2
Task_1
Task_2
Task_3
Task_4
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A